## High-level Plan
RedRose Implementation - High-Level Project Plan
Activities | Owner | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20
Analysis
Review cash process (SOP’s) with programme teams and identify data challenges or bottle necks
Documentation & prioritization of requirements or specifications
Agreement between stakeholders of requirements
Planning
Project costing
Allocating resources/teams, who’s involved
Agreeing on timeline/dates
Develop detailed implementation plan
System Setup & Testing
Configure RedRose
Install hardware & software
Test everything works as specified in demo environment
Establish technical support
Training
Prepare training materials
Conduct train the trainer (ToT)
Conduct field level training
Go-Live & Evaluation
Monitor and complete the cash or in-kind programme using RedRose
Evaluate the use of RedRose after the programme is complete

## Setup Plan
RedRose Implementation - System Setup Project Plan
Activities | Owner | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20
System Setup & Testing
Setup demo environment based on specifications - provide beneficiary registration form | RedRose | x
Setup Skype group for technical support | RedRose | x
Create roles and users in demo environment | System Admin |  | x
Test processes in demo environment, report issues to RedRose | Programme |  | x
Test dashboards in demo environment | Programme |  | x
Install hardware & software | System Admin |  | x
Test beneficiary registration using RRCollect | Programme / Volunteer |  | x
Test FSP integration | Programme |  | x
Test excel reports | Programme |  | x
Move all configuration to LIVE environment after testing is successfully completed | RedRose |  | x
Training
Prepare training materials | RedRose / Programme / System Admin |  | x
Conduct train the trainer (ToT) | RedRose or someone with RedRose experience |  |  | x
Training for Finance, Managers, PMER/IM | Programme / System Admin |  |  | x
Conduct field level training - volunteers/staff | Programme / System Admin |  |  | x
Go-Live & Evaluation
Conduct Beneficiary Registration in the field | Volunteers / Staff |  |  |  | x
Monitor data quality, cleanse data, disable duplicates | Programme |  |  |  | x
Setup fund, funding allocation, distribution activities | Programme, Finance |  |  |  | x
Setup beneficiary group and topup with entitlements, go through approval process | Programme, Finance |  |  |  | x
Confirm FSP receives cash and the payment order | FSP |  |  |  | x
Distribution of cash & reconciliation | Programme, FSP |  |  |  |  | x
Capture beneficiary feedback with RRCollect | Volunteers / Staff |  |  |  |  | x
Monitor progress of cash distribution | Programme |  |  |  |  | x
Conduct Post Distribution Monitoring | Volunteers / Staff | [6 empty] | x
Evaluate the outcomes of the programme using RedRose | Programme | [7 empty] | x