## FSPs_third parties
CVA Financial Flows Tool - FSPs/Third Parties
| Activity | Who responsible? | Authorisation needed? (Y/N) | Who authorises? (based on the NS approval system) |  |  |  | Number of days for processing/approval | Supporting documents required | Considerations/potential bottlenecks and mitigations
|  |  |  | e.g. < USD 50,000 | e.g. USD 50K - 250 K | e.g. USD 250 K- USD 1mil | e.g. > USD 1 million
|  |  |  | Finance Manager | Head of Finance | Under Sec Gen | Sec Gen/Chairman
Step 1 - Receiving of Donor Funds by NS | Sign Project Funding Agreement/Grant Agreement/donor contract | Programmes | Y | [6 empty] | Subsequent steps in the tool should be based around the PFA/GA schedule of payment, conditions of transfer and reporting requirements. e.g. For projects over CHF 1M, 50% of each transfer must be spent before a new transfer is issued.
| Request funds from donor as per agreement | Finance | Y | [6 empty] | Consider donor internal processes to authorize and transfer funds, as well as other regulations that could delay funds. Internal delays of the back donor, even within the Movement, should be acknowledged here. Consider any governments under sanctions (e.g. imposed by the donor, country of primary bank etc.)
| Deposit & code funds received from donor in NS bank account | Finance | N
Step 2 - Transfer of Funds to FSPs | Prepare Distribution Plan | Programmes | N | [5 empty] | M4_5_2_4 Distribution Plan
| Deposit funds between HQ and districts/branches per allocated # of recipients | Finance | Y | [5 empty] | M4_5_2_4 Distribution Plan
| Prepare SMART cards/bank cheques/ SIM cards etc and provide to NS | IFRC or FSP/third party | N | [5 empty] | M4_5_2_4 Distribution Plan; Waybill/DN | IFRC has a threshold for payments to third parties, which the NS should comply with for the disbursement/encashment process.
| Prepare and raise Cash Request | Finance | N | [5 empty] | M4_5_2_4 Distribution Plan
| Approve Cash Request | Finance | Y | [5 empty] | M4_5_2_4 Distribution Plan | Cash requests should be checked against supporting documentation, previous balances reconciled and any possible errors.
| Transfer funds to FSP/third parties | Finance | Y | [5 empty] | M4_5_4_1 Payment Order; M4_5_2_4 Distribution Plan | The cash request form can be adapted from CiE toolkit or the FSP may provide their own. For large programs or for ones that involve different currencies, consider sending money to the FSP in tranches to minimize risk of money sitting with the FSP and foreign exchange risk.
| FSP/third party confirms receipt of funds | FSP | N | [6 empty] | A debit note is required from the FSP since NS is an intermediary between the FSP and the beneficiary
Step 3 - Encashment | Prepare Encashment Plan and lists for FSP/third party or IFRC/NS if pre-loading (based on delivery mechanism) | Programmes | N | [5 empty] | M4_ 5_3_3 Encashment Plan; M4_5_4_2 Encashment List | As recipient names are being provided at this stage, ensure all necessary data protection protocols are in place and have been agreed between parties. Check how many days in advance NS has to initiate transfer to FSP to be ready for each encashment, as per contract.
| FSP/third party transfers payments to recipients or IFRC/NS pre-load funds directly | FSP/Finance | N | [5 empty] | M4_5_4_2 Encashment List | Understand what happens when funds are not collected by the beneficiary. How is that reverted back to the NS?
Step 4 - Reconciliation of Payments | Reconcilliation of payments made against beneficiary names/FSP invoice - per encashment/month (or as per contract) | Programmes | N | [5 empty] | Encashment Report; FSP financial report or invoice; Payment register; M4_5_5_4 Third Party Reconcilliation | Any activity related to recipients that are "add ons, unclaimed, cancelled or reissued" should be documented separately and tracked to completion. A separate record should also be kept of all discrepancies and concerns, how resolved, who handled and approved.
| Validation of FSP reconcilliation - per encashment/month (or as per contract) | Finance | Y | [5 empty] | Encashment Report; FSP financial report or invoice; Payment register; M4_5_5_4 Third Party Reconcilliation
| Investigate and resolve any oustanding discrepencies | Programmes/Finance | Y | [6 empty] | Payments or corrections may be need to made to beneficiaries with outstanding issues.
| Final reconcilliation of FSP/third parties - end of project | Finance | Y | [5 empty] | FSP MoU/agreement; M4_5_4_1 Payment Order; M4_5_4_2 Encashment List | Final reconcilliation should verify there are no outstanding discrepancies, issues or concerns, as documented above.
| Request return of unspent/undistributed funds by FSP | Finance | Y
| Payment to or return of funds by FSP/third party | FSP | N
| Confirmation of unspent funds returned and close balance | Finance | Y
Note on J3: Ruth Aggiss: So far I have only added relevant critical CiE documents. Assume there are others that can be added from finance guidelines?

## Cash by-hand
CVA Financial Flows Tool - Direct Cash by NS
| Activity | Who responsible? | Authorisation needed? (Y/N) | Who authorises? (based on the NS approval system) |  |  |  | Number of days for processing/approval | Supporting documents required | Considerations/potential bottlenecks and mitigations
|  |  |  | e.g. < USD 50,000 | e.g. USD 50K - 250 K | e.g. USD 250 K- USD 1mil | e.g. > USD 1 million
|  |  |  | Finance Manager | Head of Finance | Under Sec Gen | Sec Gen/Chairman
Step 1 - Receiving of Donor Funds by NS | Sign Project Funding Agreement/Grant Agreement/donor contract | Programmes | Y | [6 empty] | Subsequent steps in the tool should be based around the PFA/GA schedule of payment, conditions of transfer and reporting requirements. e.g. For projects over CHF 1M, 50% of each transfer must be spent before a new transfer is issued.
| Request funds from donor as per agreement | Finance | Y | [6 empty] | Consider donor internal processes to authorize and transfer funds, as well as other regulations that could delay funds. Internal delays of the back donor, even within the Movement, should be acknowledged here. Consider any governments under sanctions (e.g. imposed by the donor, country of primary bank etc.)
| Deposit & code funds received from donor in NS bank account | Finance | N
Step 2 - Prepare for Distribution | Prepare Distribution Plan | Programmes | N | [5 empty] | M4_5_2_4 Distribution Plan | Consider security risks alongside and ensure security management plan is also developed - allow time for varying transport routes, payment times etc
| Deposit funds between HQ and districts/branches per allocated # of recipients | Finance | Y | [5 empty] | M4_5_2_4 Distribution Plan
| Prepare and raise Cash Request | Finance | N | [5 empty] | M4_5_2_4 Distribution Plan
| Approve Cash Request | Finance | Y | [5 empty] | M4_5_2_4 Distribution Plan | Cash requests should be checked against supporting documentation, previous balances reconciled and any possible errors.
Step 3 - Encashment | Prepare Encashment Plan + lists per location | Programmes | N | [5 empty] | M4_ 5_3_3 Encashment Plan; M4_5_4_2 Encashment List | As recipient names are being provided at this stage, ensure all necessary data protection protocols are in place and have been agreed between parties.
| Withdraw money from bank (field) and prepare cash in envelopes: | Finance + Programmes | Y
| - Transfer money safely to branches | Finance + Programmes | N | [6 empty] | Ensure safe already in place.
| - Process money | Finance + Programmes | Y | [6 empty] | Consider availablity of 3 people for the task, e.g. 1 person counting, 2nd recounting, 3rd person cash into envelope + sign (Segregation of duties)
| - Cash put into safe | Finance | N | [6 empty] | Consider availability of a separate (4th) person to the processing (Segregation of duties)
| Cash released from safe, as per Encashment Plan | Finance | Y
| Cash transported to distribution points | Finance + Programmes | N
| Cash distribution - beneficiary cash count in front of cashier + signing of cash register | Programmes + Finance | N | [5 empty] | M4_5_4_2 Encashment List
Step 4 - Reconciliation of Payments | Reconcilliation of payments made against beneficiary names - per distribution | Programmes | N | [5 empty] | M4_5_4_2 Encashment List; Payment register; M4_5_5_4 Cash By Hand Reconcilliation | Any activity related to recipients that are "add ons, unclaimed, cancelled or reissued" should be documented separately and tracked to completion. A separate record should also be kept of all discrepancies and concerns, how resolved, who handled and approved.
| Validation of distribution reconcilliation | Finance | Y | [5 empty] | Payment register; FSP financial reports
| Final reconcilliation of cash distrbutions - end of project | Finance | Y | [5 empty] | FSP MoU/agreement; M4_5_4_1 Payment Order; M4_5_4_2 Encashment List | Final reconcilliation should verify no outstanding discrepancies, issues or concerns, as documented above.
Note on J3: Ruth Aggiss: So far I have only added relevant critical CiE documents. Assume there are others that can be added from finance guidelines?

## Vouchers
CVA Financial Flows Tool - Vouchers
| Activity | Who responsible? | Authorisation needed? (Y/N) | Who authorises? (based on the NS approval system) |  |  |  | Number of days for processing/approval | Supporting documents required | Considerations/potential bottlenecks and mitigations
|  |  |  | e.g. < USD 50,000 | e.g. USD 50K - 250 K | e.g. USD 250 K- USD 1mil | e.g. > USD 1 million
|  |  |  | Finance Manager | Head of Finance | Under Sec Gen | Sec Gen/Chairman
Step 1 - Receiving of Donor Funds by NS | Sign Project Funding Agreement/Grant Agreement/donor contract | Programmes | Y | [6 empty] | Subsequent steps in the tool should be based around the PFA/GA schedule of payment, conditions of transfer and reporting requirements. e.g. For projects over CHF 1M, 50% of each transfer must be spent before a new transfer is issued.
| Request funds from donor as per agreement | Finance | Y | [6 empty] | Consider donor internal processes to authorize and transfer funds, as well as other regulations that could delay funds. Internal delays of the back donor, even within the Movement, should be acknowledged here. Consider any governments under sanctions (e.g. imposed by the donor, country of primary bank etc.)
| Deposit & code funds received from donor in NS bank account | Finance | N
Step 2 - Transfer of Funds to FSPs | Prepare Distribution Plan | Programmes | N | [5 empty] | M4_5_2_4 Distribution Plan
| Deposit funds between HQ and districts/branches per allocated # of recipients | Finance | Y | [5 empty] | M4_5_2_4 Distribution Plan
| Create or procure vouchers | Programmes/Procurement | N | [5 empty] | M4_5_2_4 Distribution Plan; Waybill/DN | IFRC has a threshold for payments to third parties, which the NS should comply with for the disbursement/encashment process.
Step 3 - Encashment | Prepare Encashment Plan and lists for traders or IFRC/NS if pre-loading (based on delivery mechanism) | Programmes | N | [5 empty] | M4_ 5_3_3 Encashment Plan; M4_5_4_2 Encashment List | As recipient names are being provided at this stage, ensure all necessary data protection protocols are in place and have been agreed between parties. Check how many days in advance NS has to initiate transfer to FSP to be ready for each encashment, as per contract.
| Voucher redemption/encashment | Traders/third parties | N | [5 empty] | M4_5_4_2 Encashment List
Step 4 - Reconciliation of Payments | Reconcilliation of vouchers and encashment - weekly/daily depending on encashment plan | Programmes | N | [5 empty] | Trader financial reports; M4_5_5_4 Third Party Reconcilliation; Any returned physical vouchers | Any activity related to recipients that are "add ons, unclaimed, cancelled or reissued" should be documented separately and tracked to completion. A separate record should also be kept of all discrepancies and concerns, how resolved, who handled and approved.
| Validation of voucher reconcilliation | Finance | Y | [5 empty] | Trader financial reports; M4_5_5_4 Third Party Reconcilliation; Any returned physical vouchers
| Trader generates invoice for payment - monthly (or as per contract) | Trader/third party
| Validation and payment of trader invoice | Finance | Y | [5 empty] | Trader invoice; M4_5_5_4 Third Party Reconcilliation
| Trader confirms receipt of invoice payment | Trader/third party | N
| Investigate and resolve any oustanding discrepencies | Programmes/Finance | Y | [6 empty] | Payments or corrections may be need to made to beneficiaries with outstanding issues.
| Final reconcilliation of traders - end of project | Finance | Y | [5 empty] | Trader MoU/agreement; Trader invoices, Final beneficiary list; Trader financial reports; M4_5_5_4 Third Party Reconcilliation | Final reconcilliation should verify no outstanding discrepancies, issues or concerns, as documented above.
| Payment to or return of technology to traders (as per contract) | Finance | Y | [5 empty] | Trader MoU/agreement; Trader invoices, Final beneficiary list; Trader financial reports; M4_5_5_4 Third Party Reconcilliation
Note on J3: Ruth Aggiss: So far I have only added relevant critical CiE documents. Assume there are others that can be added from finance guidelines?