Example 2.1.3 - Log Frame Rental Assistance

*Note: this is the edited version of a real example of a draft logical framework from the rental assistance programme in Poland as part of the Ukraine 2022 response*

**Polish Red Cross-IFRC Shelter Programme in Poland**

**Cash for Rent Assistance for Ukrainian displaced households and Polish Vulnerable families**

**Logical Framework - DRAFT**

|  |  |  |
| --- | --- | --- |
| **Goal:** Displaced people and Polish vulnerable families are supported with cash for rental assistance in line with governmental policies. | | |
| **Objectives** | **Indicator** | **Means of Verification** |
| **Outcome 1:**  Displaced households (refugees from Ukraine and third country nationals) receive support to rent accommodations between 6 and 9 months. | -100 % of programme recipients have access to rental accommodation through provision of cash.  - 80% of the programme recipients who are satisfied with the accommodation accessed through the cash support | -Post-distribution monitoring/ feedback surveys/evaluations |
| Output 1.1: Lodz  30 displaced households who are staying in German Red Cross funded hostel have access to rental accommodation during the project period that has secure tenure, meets minimum housing standards and is connected to essential services, markets and livelihood opportunities. | - 30 of households that have the rental agreements  - 30 of households who have had their accommodation checked to ensure it meets the minimum housing standards and standards related to access to services, markets and livelihoods. | - Home visits and surveys to those in rented homes.  - Signed agreements with beneficiaries and landlords.  -Inclusion Officers observation records  -List of people referred as programme recipients  - Feedback and evaluation reports  -baseline and endline evaluation with beneficiaries |
| Output 1.2: Warsaw  150 displaced households staying in the Government funded collective shelter have access to rental accommodation during the project period that has secure tenure, meets minimum housing standards and is connected to essential services, markets and livelihood opportunities. | - 100 (non minority heritage households, such as Roma) of households that have the rental agreements  - 100 (non minority heritage households, such as Roma) of households who have had their accommodation checked to ensure it meets the minimum housing standards and standards related to access to services, markets and livelihoods.  - 50 displaced (minority heritage households, such as Roma) households have rental agreements,  - 50 displaced (minority heritage households, such as Roma) have had their accommodation checked to ensure it meets meet minimum housing standards and standards related to access to services, markets and livelihoods. | - Family visits and surveys in rented homes.  - Signed agreements with beneficiaries and landlords.  -Inclusion Officers observation records  -List of people referred as programme recipients  - Feedback and evaluation reports  -baseline and endline evaluation with beneficiaries |
| **Outcome 2:**  Displaced households (refugees from Ukraine and third country nationals) maintain rental accommodation after completion of the rental assistance programme. | 80% of the programme recipients  continue renting the same or a different accommodation after the rental support has ceased. | PDM undertaken 1 to 3 months after end of supported rental period. |
| Output 2.1: Programme recipients who are referred to the Integration Centre are assisted to improve their employability increasing their potential for income. | 50% of programme recipients benefitting from the integration centers who reported that the support that the integration centers provided contribute to them finding a job. | - List of referred programme recipients  - Feedback and evaluation reports  -Recipient satisfaction surveys |