## Shelter
Example 3.2 - Shelter Indicators
Note: this is a real example of indicators used in the Hurrican Dorian Response in 2019 in the Bahamas.
| AoF | APCode | Activity (Budget) | Outcome / Output |  | Indicator / Activity | Target | Unit of Measurement | Total Progress | NP | GB | AB | % | Updated | Source | # women | # men | Comentarios
| Shelter |  |  | Shelter - Outcome 1 | 1.a | % of surveyed people who report that the shelter solution they implemented has helped in their longer-term recovery | 80 | % | 0% | 0 | 0 | 0 | 0% |  | Exit survey for repairs and rental
| Shelter |  |  | Shelter - Output 1.1 | 1.1.a | # of households provided with emergency shelter and settlement assistance (shelter toolkits, tarpaulin, kitchen sets, cleaning sets and blankets) | 2000 | households | 2316 |  |  |  | 115.8% |  | IM map, procured items from finance
| Shelter | AP005 |  | Shelter - Output 1.1 | 1.1.b | # displaced households provided with mid-term shelter and settlement assistance through cash and voucher assistance (rental support) | 235 | households | 193 |  | 193 |  | 82.13% | 2020-04-02 | Rental dashboard, rental database |  |  | Families that have received at least 3 chques
| Shelter | AP005 |  | Shelter - Output 1.1 | 1.1.c | # households provided with shelter assistance to repair non structurally damaged homes. | 500 | households | 20 |  | 20 |  | 4% | 2020-04-02 |  |  |  | number of cheques delivered / total number of cheques to be disbursed.
| Shelter | AP005 |  | Shelter - Output 1.1 |  | Coordination with government and other stakeholders | [6 empty] | #DIV/0! |  | updates
| Shelter | AP005 |  | Shelter - Output 1.1 |  | Assessment of immediate and early recovery shelter needs, capacities and gaps, and mid-term shelter solutions, including market assessments. | ? | assessment |  |  |  |  | #VALUE! |  | assessment reports
| Shelter | AP005 |  | Shelter - Output 1.1 |  | Identification of target families during the emergency phase provided with household items | [6 empty] | #DIV/0! |  | beneficieary list
| Shelter | AP005 |  | Shelter - Output 1.1 |  | Procurement and distribution of emergency shelter and household items (tarpaulins, light blankets, kitchen sets, toolkits, cleaning kits) | 2000 | kits |  |  |  |  | 0%
| Shelter | AP005 |  | Shelter - Output 1.1 |  | Identification of target families to be provided with medium term shelter and settlement needs – 235 Rental grants | 235 | households |  |  |  |  | 0% |  | enrolment list, agrremnt signed
| Shelter | AP005 |  | Shelter - Output 1.1 |  | Provision and monitoring of rental grants on a monthly basis for 6 months | 235 | households | 0% | 0 | 193 | 0 | 0% | 2020-04-02 | proof of payment, contract signed
| Shelter | AP005 |  | Shelter - Output 1.1 |  | Identification of target families to be provided with safe, sustainable and secure settlement conditions - Repairs for 500 homes | 500 |  |  | 0 | 20 | 0 | 0% |  | enrolment list, agrremnt signed
| Shelter | AP005 |  | Shelter - Output 1.1 |  | Repair of homes to support safe, sustainable and secure settlement conditions for 500 families and monitoring | 500 |  |  | 0 | 10 | 0 | 0% |  | progress reports
| Shelter | AP005 |  | Shelter - Output 1.1 |  | Assess improvement of community spaces near the location of house repairs | 2 |  |  | 0 | 0 | 0 | 0% |  | completion report
| Shelter | AP006 |  | Shelter - Output 1.2 | 1.2.a | # of community members that received orientation on Build Back Safer | 500 | persons | 0 | 0 | 0 | 0 | 0% |  | attendence sheet |  |  | Verify if it's a training or alea flets?
| Shelter | AP006 |  | Shelter - Output 1.2 | 1.2.b | % of surveyed people demonstrate knowledge of safer building practices in their shelter solutions | 80 | % | 0 | 0 | 0 | 0 | 0% |  | Exit survey for repairs and rental
| Shelter | AP006 |  | Shelter - Output 1.2 | 1.2.c | # of BRCS volunteers and staff trained in Build Back Safer, All under one Roof and PASSA ToT | 20 | people | 10 | 0 | 10 | 0 | 50% |  | Training activity report
| Shelter | AP006 |  | Shelter - Output 1.2 |  | Production and distribution of (information, education and communication) IEC materials for 500 families | 500 | leaflets? | 0 | 0 | 0 | 0 | 0% |  | list of material
| Shelter | AP006 |  | Shelter - Output 1.2 |  | Orientations on assessments implementation for volunteers |  | volunteers | 0 |  |  |  | #DIV/0! |  | attendence sheet
| Shelter | AP006 |  | Shelter - Output 1.2 |  | Orientations to volunteers on the best use of the distributed shelter and household items |  | volunteers | 0 |  |  |  | #DIV/0! |  | not needed now
| Shelter | AP006 |  | Shelter - Output 1.2 |  | Orientations to affected households on the best use of the distributed shelter and household items | 2000 | households | 0 |  |  |  | 0% |  | leaflets distribruted
| Shelter | AP006 |  | Shelter - Output 1.2 |  | Development of rental assistance guideline & case study | 2 | document | 0 |  |  |  | 0% |  | copy of guidelines
| Shelter | AP006 |  | Shelter - Output 1.2 |  | Evaluation/ lessons learned workshop on shelter response | 1 | workshop | 0 |  |  |  | 0%
| Shelter | AP006 |  | Shelter - Output 1.2 |  | Regional technical shelter focal point monitoring visits |  | visits | 0 |  |  |  | #DIV/0!
| Shelter | AP006 |  | Shelter - Output 1.2 |  | Regional support 6 months | 6 | months | 7 |  |  |  | 116.7%
| Shelter | AP006 |  | Shelter - Output 1.2 |  | Trainings for construction professionals and the community on Build Back Safer |  |  | 0 |  |  |  | #DIV/0! |  | training report
| Shelter | AP006 |  | Shelter - Output 1.2 |  | Training of Trainers on Participatory Approach for Safe Shelter Awareness (PASSA) Youth/Plus |  |  | 0 |  |  |  | #DIV/0! |  | training report
| Shelter | AP006 |  | Shelter - Output 1.2 |  | Training of All Under One Roof for staff and volunteers |  | training | 0 |  |  |  | #DIV/0! |  | training report
| Shelter | AP006 |  | Shelter - Output 1.2 |  | PASSA Youth/Plus sessions for affected households |  | training | 0 |  |  |  | #DIV/0! |  | not needed
| Shelter | AP006 |  | Shelter - Output 1.2 |  | Staffing cost for shelter (2 delegates Abaco + Grand Bahama) national staff, and daily workers) | 12 | persons | 5 | 1 | 3 | 1 | 41.67%
Note on G5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Will we include rental for this indicator?