## Summary
Example 2.1.6 Payments Forecast
Note: This is an example of a simple table used to forecast rental payments to show cumulative number of transfers that may take place each and total value of those payments. Could be helpful to generate similar to aid discussion with finance.
Summary Information On Rental Payments
Item | Value & Unit | Notes
Duration of programme | 18 months | From Assessment to Evaluation
Overall number of households to be supported | 500 households | Enrolled over 6 months of the programme.
Rental payment supported period | 6 months, for 10% of households they will be supported for a further 3 months. | However, note that some households may exit programme early if they return / move on etc.
Payment to | Target (tenant household)
Transfer Mechanism | MoneyGram (via. RedRose) to Tenant bank accounts (Euro accounts). | Only households with a Euro bank account in a local bank will be allowed to enrol on the programme. Those without will be assisted to open Euro bank account in a local bank.
Monthly rental payment range | 400 Euro – forecast 33% of households 500 Euro - 33% 600 Euro – 33% | Depending on household composition.
Paid at start of tenancy and then at one month intervals at the payment date decided by tenancy agreement.
Deposit payment | 1 month of rent equivalent | Paid at start of tenancy only. Will not be returned to RC but will be returned to tenant.
Move-in grant | 200 Euro | Paid at start of tenancy only
Budget allowance for age and disability adaption | 500 Euro for 15% of Households

## Forecast
| 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2024 | 2025 | 2026
Month | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep
New Households Enrolled on Programme | Jun: 0; Jul: 40; Aug: 60; Sep: 100; Oct: 100; Nov: 100; Dec: 100
Cumulative No. of households receiving additional 3 months support | Jan: 4; Feb: 10; Mar: 20; Apr: 26; May: 30; Jun: 30; Jul: 20; Aug: 10; Sep: 0
Cumulative No. Households receiving rental payments | 0 | 40 | 100 | 200 | 300 | 400 | 500 | 464 | 410 | 320 | 226 | 130 | 30 | 20 | 10 | 0
Budget spend for age and disability allowance / Euro | Jul: 3000; Aug: 4500; Sep: 7500; Oct: 7500; Nov: 7500; Dec: 7500
Cumulative Transfer Value / Euro |  | 51000 | 96500 | 177500 | 227500 | 277500 | 327500 | 232000 | 205000 | 160000 | 113000 | 65000 | 15000 | 10000 | 5000
This form is setup as an example, all formula should be re-established when using this for your programme.