## Risk register
Example 2.1.9 Risk Assessment Register
Note: This is a real example of a risk assessment register used in Slovakia for the Ukraine 2022 response
Risk no: | Country / CCST | Project | Strategic Priority | Risk Category | Risk Driver / Root cause | Risk description | Risk consequences / Impact | Inherent Impact | Inherent Likelihood | Inherent Risk Factor | Current Controls (Mitigation) | Perceived effectiveness of controls | Residual Impact | Residual Likelihood | Residual Risk Factor | Proximity | Acceptable risk? | Risk Response Strategy | Additional Controls (what further action are we planning to put in place?) | Cost of additional Controls | Impact of additional controls | Estimated implementation date of additional controls | Risk Owner | Risk Status | Risk Trend | Last Updated | Thematic Areas | Risk unique ID
2 |  |  |  | Programme Delivery |  | Landlords not interested in short term rent: Due to a short-term contract, landlords are not willing to rent to refugees, resulting in limited rental opportunities available to refugees. |  | 3 | 2 | 6 | *Top up incentives for landlords: 400 euro lump sum for housing repairs at the start of the contract (lump sum meaning landlords can keep the part not used for repairs); 300 euro after first 2 months; | Good | 1 | 1 | 1 | Within 6 months | Y | Treat | more focus on hosting families | no | no | concurent | shelter delegate | Open |  | 2023-03-14 |  | -2
3 |  |  |  | Contextual |  | Limited programme funds: Winter and/or escalation of violence in Ukraine lead to a high volume of new arrivals seeking shelter support resulting in programme inability to provide support to all eligible refugees. |  | 4 | 1 | 4 | Programme budget is monitored and revised accordingly | Very good | 1 | 1 | 1 | [8 empty] | Open |  | 2023-03-14 |  | -3
4 |  |  |  | Programme Delivery |  | Exit strategy: The programme does not have a sufficient exit strategy in place, undermining long term positive impact of the programme. (ie. Refugees unable to self-finance rent and have to move out, exacerbating their vulnerability). |  | 2 | 4 | 8 | Exit strategy has been developed and and many activities which can increase the potential of sustaining accommodation, but there are many factors which influence the exit and beyond the scope of the project | Weak | 3 | 3 | 9 | Greater than 6 months | Y | Tolerate | *Complementary programming programming - e.g. livelihoods / support with finding employment or obtaining legal documents for work. * Mapping referral pathways for alternative accommodation options for refugees *Close collaboration with government authorities at national and at local levels to find alternative accommodation options. |  |  |  | shelter delegate |  |  | 2023-03-14 |  | -4
5 |  |  |  | Contextual |  | Tensions with host communities: Due to growing economic hardships across host communites, there is a risk that tensions with host communities arise and lead to a declining support for SRC / IFRC, potentially undermining the programme ability to operate. |  | 2 | 2 | 4 | Slovak Red Cross is also supporting hosting communities to increase the social cohesion between two communities. | Satisfactory | 2 | 2 | 4 | Within 6 months | [9 empty] | 2023-03-14 |  | -5
6 |  |  |  | Operational |  | External comms strategy:The programme does not have an appropriate communications package in place, leading to false information about the programme being circulated. This acts as a deterrrent for refugees to apply to the programme and could ultimately harm SRC / IFRC reputation. |  | 3 | 2 | 6 | all the progarmmme documents I.e. agreements, announcements, programme dissemination documents clearly states the duration of the assistance. | Very good | 1 | 1 | 1 | Within 3 months | [9 empty] | 2023-03-14 |  | -6
[6 empty] | Displaced hh leave the accomodation before agreement duration and relocate or return |  | 4 | 3 | 12 | Clear explanation to the displaced HH on the prograame, the implication of not following the agreement condition and if return is planned, HSPs should be informed in advance, to make arrangement with LL. | Weak | 3 | 2 | 6 | Within 6 months | Y | Tolerate |  |  |  |  | shelter delegate |  |  | 2023-03-14 |  | -
7 |  |  |  | Contextual |  | Rental market Inflation: Due to inflation, rental market prices surpass the agreed payment calculations for the programme and lead to difficulties for programme team and refugees to identify properties with suitable price. This has adverse impact on the number of families we are able to support. |  | 3 | 3 | 9 | continues monitoring of the situation and agility of the programme to accommodate inflation affect in the rental value has been considered. Increasing hosting solutions | Satisfactory | 3 | 2 | 6 | Within 6 months | Y | Treat | Options: *continuous monitoring of the market prices and recalculation of rental payments if needed? (could also say that the monitoring of market prices is conducted through refugee feedback on a continuous basis and if we find that properties are too expensive, we recalculate?) |  |  |  | shelter delegate | Open |  | 2023-03-14 |  | -7
8 |  |  |  | Contextual |  | False expectations:Limited understanding of the programme creates false expectations (e.g. guaranteed accommodation, longer term support from SRC, etc) This could ultimately lead to delays in individual stages of the programme or harm RC reputation among refugees. |  | 2 | 2 | 4 | *Roles and requirements on refugees, landlord and SRC clearly outlines in tripartite agreement. Also, a message stating the termination of the assistance is sent to the beneficiaries two months prior to the termination of the assistance. | Satisfactory | 1 | 1 | 1 | Within 6 months |  |  | *SRC volunteers provided with training that covers, among other things: A core script on what info to share with refugees when they arrive at the branch for a registration; Answers to frequently asked questions including handling difficult situations (e.g. dealing with upset families not admitted to the programme) Info note for the volunteers explaining key definitions and concepts that are in the registration form (e.g. single headed household, unaccompanied women etc.) |  |  |  |  | Open |  | 2023-03-14 |  | -8
9 |  |  |  | Operational |  | SRC capacity: HSP do not have sufficient human resourcing capacity to ensure timely and effective running of the programme. This could lead to delays in submitting requests for payments and ultimately harm relationships with landlords / refugees. |  | 3 | 4 | 12 | currently, the staff is sufficient to implement the activities, however there is need to assess this capacity and see whether, this sufficiency will be maintained in futures when there will be multiple activities to be implemented by HSP staff i.e. cash for health, livelihoods, language, MPHSS etc. | Weak | 3 | 2 | 6 | Within 3 months | Y | Treat | *Use info and insights from the pilot to determine the duration of each step of the programme and compare this to the number of volunteers in each branch vs the target number of registration. *Assess the capacity in each branch vis a vis the duration of each step in the programme process (e.g. registration, housing standard visit, monitoring visits etc.) to ensure realistic and managable workload on each branch and adjust programme expectations accordingly. |  |  |  |  | Open |  | 2023-03-14 |  | -9
[6 empty] | Dealy in paymnet of rental and top-up to beneficiaries |  | 4 | 2 | 8 | The situation will be continously monitored, the payment will be submitted one week before to the MG to allow them 7 warking days. (The MG payment time is minimum 48 hours starts from the paymnet submission and maximum is 7 days) |  |  |  | 0 |  |  |  | alternate plan for the payment in case the existing system male functions | [8 empty] | -
10 |  |  |  | Operational |  | Circumvention of processes: Volunteers assume responses to questions during registration compromising the reliability of collected information. This could compromise the accuracy of the assessment process and lead to false admissions / exclusions. Where aditional questions are asked to inform design of future programming (e.g. questions about additional refugee needs) this could skew our understanding of refugees needs and misinform design of future complementary programming. |  | 3 | 2 | 6 | staff and volunteers have been trained and close monitoring and technical backstopping from the HQ is available to HSPs, a weekly call is conducted and vols and staff are sensitized on such issues. | Good | 1 | 1 | 1 | Within 1 month | [7 empty] | Open |  | 2023-03-14 |  | -10
11 |  |  |  | Operational |  | Process for 3 months additional support: Process to extend support for 3 months for vulnerable cases not yet designed. |  |  |  | 0 | Not applicable now |  |  |  | 0 | [8 empty] | Closed |  | 2023-03-14 |  | -11
12 |  |  |  | Safeguarding (Sexual exploitation and abuse (external) and sexual harassment (internal)) |  | SEAH: Service users are exposed to sexual exploitation and abuse, resulting in harm to individuals, loss of trust in the Movement, loss of donor confidence and ultimately undermining our ability to operate. |  | 5 | 2 | 10 | Red Cross helpline is available to all the progarmme participants and also there are monthly calls conducted by HSP staff to the beneficiaries and protection risks are monitored. Protection, gender and inclusion question are asked during the calls. | Satisfactory | 2 | 3 | 6 | Within 6 months | N |  | PGI Trainings for the satff and volunteers | 0 | not started yest | April | shelter delegate |  |  | 2023-03-14 |  | -12
13 |  |  |  | Safeguarding (Sexual exploitation and abuse (external) and sexual harassment (internal)) |  | Capability to respond to SEAH: Programme staff and volunteers do not have appropriate training and skills to effectively respond to SEAH allegations and disclosures from refugees, limiting their ability to apply survivor centred approach when responding, failing to provide appropriate support and ultimately causing unintended harm to survivors of abuse. |  | 3 | 3 | 9 | the programme has limited scale and within the given scale and SEAH prevalence trend, with the support from IFRC delegates and HQ, SEAH can be managed upon triggering the issues. |  | 2 | 3 | 6 | Within 6 months | Y |  | PGI Trainings for the satff and volunteers | 0 | not started yest | April | shelter delegate | Open |  | 2023-03-14 |  | -13
14 |  |  |  | Operational |  | Clarity on roles and responsibilities: There is a risk that roles and responsibilities within each SRC branch are not clearly set out, causing confussion and delays in implementing programme effectively and efficiently. |  | 2 | 1 | 2 |  |  |  |  | 0 | Within 1 month | [7 empty] | Closed |  | 2023-03-14 |  | -14
15 |  |  |  | Operational |  | Data monitoring: There is a risk that we do not systematically and consistently review data and miss the opportunity to continuously enhance / adjust the effectiveness of the intervention. |  | 1 | 1 | 1 |  |  |  |  | 0 | Greater than 6 months | [9 empty] | 2023-03-14 |  | -15
16 |  |  |  | Programme Delivery |  | Limited ability to support marginalised groups: There is a risk that marginalised groups (e.g. minorities, disabled) may face additional challenges when looking for accommodation, limiting our ability to effectively support their shelter needs. |  | 3 | 2 | 6 | Programme is open for displaced people from Ukraine and it has vulnerability criteria which is inclusive and is being disseminated through announcement and other dissemination activities | Good | 2 | 1 | 2 | Within 6 months |  |  | What additional support can we provide to minorities, disabled? |  |  |  |  | Closed |  | 2023-03-14 |  | -16
17 |  |  |  | Operational |  | GDPR / data protection: Significant non compliance with relevant data protection regulations, including GDPR, leading to penalties |  | 5 | 1 | 5 | only the minimum identifiable data is collected from the beneficiaries, and protection measures are in place in espoCRM which is the case management system for this programme undertaking and information | Very good | 3 | 1 | 3 | Greater than 6 months | [7 empty] | Closed |  | 2023-03-14 |  | -17
18 |  |  |  | Fiduciary |  | ForEx: Currency fluctuations impact IFRC's ability to deliver and meet oversight and financial commitments. |  | 1 | 1 | 1 |  |  |  |  | 0 | [10 empty] | 2023-03-14 |  | -18
19 |  |  |  | Fiduciary |  | Fraud: Funding is used fraudelently or for unintended purposes, resulting in reputational damage, financial loss, loss of trust among donors. |  | 4 | 1 | 4 | strict measures are in place to identify, and verify the landlords and tenants, shelter adequacy visits, collection of property ownership documents and random monitoring visits to the property helps monitor and control this factor. | Good | 2 | 2 | 4 | Within 3 months | [9 empty] | 2023-03-14 |  | -19
20 |  |  |  | Fiduciary |  | Fraud (collusion between landlord / volunteers): There is a risk that ghost beneficiaries are created and registered, allowing individuals to defraud the system. |  | 3 | 2 | 6 | strict measures are in place to identify, and verify the landlords and tenants, shelter adequacy visits, collection of property ownership documents and random monitoring visits to the property helps monitor and control this factor. | Good | 2 | 1 | 2 | Within 1 month | [11 empty] | -20
17 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -17
18 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -18
19 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -19
20 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -20
21 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -21
22 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -22
23 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -23
24 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -24
25 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -25
26 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -26
27 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -27
28 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -28
29 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -29
30 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -30
31 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -31
32 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -32
33 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -33
34 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -34
35 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -35
36 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -36
37 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -37
38 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -38
39 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -39
40 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -40
41 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -41
42 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -42
43 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -43
44 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -44
45 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -45
46 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -46
47 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -47
48 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -48
49 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -49
50 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -50
51 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -51
52 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -52
53 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -53
54 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -54
55 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -55
56 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -56
57 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -57
58 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -58
59 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -59
60 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -60
61 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -61
62 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -62
63 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -63
64 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -64
65 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -65
66 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -66
67 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -67
68 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -68
69 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -69
70 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -70
71 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -71
72 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -72
73 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -73
74 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -74
75 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -75
76 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -76
77 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -77
78 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -78
79 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -79
80 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -80
81 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -81
82 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -82
83 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -83
84 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -84
85 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -85
86 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -86
87 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -87
88 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -88
89 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -89
90 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -90
91 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -91
92 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -92
93 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -93
94 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -94
95 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -95
96 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -96
97 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -97
98 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -98
99 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -99
100 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -100
101 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -101
102 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -102
103 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -103
104 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -104
105 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -105
106 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -106
107 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -107
108 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -108
109 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -109
110 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -110
111 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -111
112 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -112
113 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -113
114 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -114
115 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -115
116 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -116
117 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -117
118 | [9 empty] | 0 |  |  |  |  | 0 | [12 empty] | -118
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Risk Evaluation Criteria
LIKELIHOOD | Risk Management Map
| Event is expected to occur in most circumstances | >90% | Almost Certain | 5
| Event could occur probably in most circumstances | 50-90% | Likely | 4
| Event should occur at some time | 30-50% | Possible | 3
| Event could occur at some time | 10-30% | Unlikely | 2
| Event may occur only in exceptional circumstances | <10% | Rare | 1
[5 empty] | 1 | 2 | 3 | 4 | 5
|  |  | Missed Targets |  | 0-5% | 5-10% | 10-20% | 20-30% | More than 40%
|  |  | Reputation |  | Internal publicity | National publicity (instance) | Extended national publicity | International publicity (instance) | Extended international publicity
|  |  | Compliance |  | Minor admonition | Minor penalties | Major penalties | Major censure | Closure
|  |  | Safety and Security |  | Minor injury | Serious injury | Multiple injuries | Single death | Multiple deaths
|  |  | Financial (% of reserves, USD) |  | 0.1% 60,000 | 0.1 to 1% 60 - 600,000 | 1-5% 600,000 - 3 Mi. | 5-25% 3 - 15 Mi. | More than 25% more than 15 Mi.
|  |  | Financial (% of program budget) |  | 0.1% | 0.1 to 1% | 1-5% | 5-25% | More than 25%
|  |  | Management Effort required to manage the impact of the event |  | Event managed through normal activity | Event whose consequencies are absorbed by additional management effort | Significant event that is managed by little additional effort | Significant event that needs substantial management effort | Catastrophic event forcing closure
IMPACT

## Terminology
Name | Definition
Risk | Any event that will have an impact on the achievement of objectives. Risk is measured in terms of impact and likelihood. Risk can have both a positive or negative impact on our goals.
Risk Description | Risks descriptions in the risk register should set out the cause and effect of the risk. A good place to begin is by considering what the objective is and then thinking about how potential risks could impact this. This aims to make clear what the consequences of a risk are. It requires a subjective judgement to set the level of risk, but it should indicate what is important to the IFRC objective (global, regional, country or project).
Risk Management | The role of risk management is to help IFRC achieve our objectives in an uncertain world. We do this by identifying, assessing, and controlling risk to our strategic, regional, country, and programmatic objectives. These threats, or risks, could stem from a wide variety of sources, including political and financial uncertainty, legal liabilities, management errors, accidents, operational system weakness, resourcing and talent challenges, and our own unique operating contexts. Ultimately the role of risk management is to support us to focus not just on the current challenges we are dealing with but to help us to anticipate and address incoming challenges as well. Moving from a focus on "firefighting" to a consideration of medium - and longer- term challenges and opportunities
Risk Registers | Risk registers enable risks, and how we are managing them, to be clearly identified, including who is responsible for monitoring and reporting on them. They should be regularly discussed and updated as this enables the sharing of knowledge on risk. The risk register will change over time, reflecting the changing context and maturity of the programme. It should clearly set out regular review points.
Risk Category | Risk categories describe causes and types of risk that fall into common groups. In IFRC we use contextual; programmatic; fiduciary; operational reputational; and sexual exploration, abuse, and harassment as risk categories. Definitions of each can be found on Tab Three "Risk Category"
Risk Driver | Basically the root cause of a risk. Something existing in our operating or programmatic environment that leads us to believe that a particular risk would occur. For example new legislation we have to meet, changes in political climates, economic downturn (local or local), change in donor expectations etc.
Risk consequence/impact | What would be the qualitiative impact on IFRC objectives, should the risk occur?
Inherent Risk | The level of risk occurring before any actions management has taken to alter the risk’s impact or probability
Residual Risk | This is the rating given to the risk after taking into account the action (mitigations) that has been taken to change the risk’s impact and probability.
Impact (of the risk on IFRC's objectives) | This is how IFRC objectives will be impacted, should the risk happen. The impact can be positive or negative, and can include direct or indirect effects of the risk. Impact can be mapped onto the five point scale on the risk map in tab four. The scale of impact ranges from "Insignificant" to "Catastrophic".
Likelihood (of the risk occurring) | Likelihood is an assessment of how likely the risk is to happen. We assess likelihood on a five point scale on the risk map on tab four. The scale ranges from 'rare' to 'almost certain'.
Controls | Controls are what we are doing to reduce or alter the impact/likelihood of the risk .
Risk appetite | This is the amount and type of risk that IFRC is prepared to accept or be exposed to, at any point in time, in the pursuit of our objectives. It is the way we express the limits of risk that can be taken or tolerated depending on the current operating context. It can include the level of exposure which IFRC would tolerate if a threat is realised or how much IFRC would actively invest in risk to realise the benefits of an opportunity.
Risk appetite can change over a period of time due to circumstances and should therefore be reviewed regularly. It will also vary for different activities and operations across IFRC. Risk appetite should be clearly articulated at the beginning of any work, to provide direction on how risks can be addressed and managed. Having an articulated risk appetite will enable us to be clearer about when to escalate and delegate) risks. For example, it can guide when risk should be escalated from a Country Office to the Reginal Office, or from a Region to the central team in Geneva. It will also help support and drive decisions making at all levels.
Risk appetites should be developed via consultation first centrally between regional directors and the USG, and at regional level between Regional Directors and their respective County Office Heads . This discussions should take into consideration partner (NS) and donor risk appetites, risk expectations and risk reporting requirements, which again may change over time.
Risk Owners | This is the individual who is ultimately accountable for ensuring the risk is managed appropriately. There may be multiple personnel who have direct responsibility for, or oversight of, activities to manage each identified risk. They will collaborate with the accountable risk owner in their effort to manage the risk.
Strategic Priority | Which of the IFRC 2030 Strategic Priorities can the risk potentially impact?
Project | Insert the relevant project code
Proximity | Within what timeframe will the risk occur, if it happens?
Acceptable risk | Is the level of the risk acceptable within the IFRC risk appetite?

## Risk Category
Contextual | Refers to events, factors or dynamics occurring in the broader environment which affect programming or operations yet are beyond the full control of IFRC (Political unrest, economic failure, famine, war, etc.). PESTEL is a helpful tool for assessment of context risk (political, economic, social, technological, environmental, legal)
Programme Delivery | Future events may negatively impact a program’s performance, schedule, cost. Also includes the risk that our programmes cause harm to our beneficiaries or their environments.
Fiduciary | The risk that funds, goods and services are not used for the intended purposes; do not achieve value for money, and are not adequately accounted for (included risk relating to fraud and corruption).
Operational | The risks to IFRC objectives arising from inadequate or failed internal processes (procurement, HR, Finance, IT etc.); inadequate or people and resourcing risks (includes risk from commercial disputes, staff shortages, supply chain shortages, staff safety, partner capacity etc.).
Reputational | The potential for negative publicity, public perception, or uncontrollable events to harm IFRC’s reputation (global, regionally or in-country), therefore affecting our ability to complete our mission (loss of donor support, partner/government disengagement, beneficiary distrust etc.).
Safeguarding (Sexual exploitation and abuse (external) and sexual harassment (internal)) | The risk that our staff, partner staff, volunteers, or beneficiaries suffer sexual exploitation, abuse, or harassment due to IFRC funding or operations.
Strategic | Inappropriate policies, failure to meet expectations/requirements of NS/donors and other stakeholders.
Note - The list is not exhaustive and risks can fit into more than one category. The focus should be on capturing the risk and recognising that risk can, and does happen throughout the strategic ,tactical or programme life cycle

## Introduction to risk management
Introduction
Risk management should be one of the cornerstone of IFRC good governance and sound management structures. It should provide the framework within which the achievement of IFRC’s objectives are managed and delivered. IFRC takes its responsibilities to its beneficiaries, partners, and donors seriously, and regards risk management as a tool of good management and an important factor in ensuring that we meet our obligations to the Movement donors and ultimately our beneficiaries.
Purpose of refreshing our risk management approach
This template is designed to:
1) Start the process of promoting and expanding the guidance to IFRC staff on the risk management processes..
2) Set out the de-minimis features of the framework and the structure of risk management within the Federation.
3) Provide a standardised template for the identification and documentation of risks, in a standard risk register.
4) Develop common terminology for risk management in IFRC.
Where are we on risk?
We all manage risk at work and in our daily lives. For example we consider the impact and likelihood of rain and decide whether to purchase or take an umbrella with us. This is true in our work lives too. IFRC manages risk every day through its country offices, regional offices and central corporate and operational teams - steered by the Senior Management Team and the Board. Risks flow from objectives and represent the uncertainty around the achievement of objectives. Despite IFRC being highly ambitious, it has been able to avoid significant risks coming to fruition and significant failures occurring. So we are collectively managing risk. IFRC is also naturally resistant to risk as our project portfolios have a hedge effect (it is hard for everything to go wrong at once). This makes IFRC more risk resilient. Over time, donor expectations have grown to expect a more formalised approach to risk management. Additionally the complexity, reach, and ambition of the Federation has grown to a point where a more standardised approach to risk management is needed.
What can we do better?
Systematisation
Whilst IFRC undertakes risk management activities, these lack systematisation and coherence across the organisation. Some risks are more structured in their management than others. For example, duty of care and security risks are more strongly controlled, and our efforts to manage it is more organised. Business risks (that is general risks to our objectives, most often project delivery objectives) are less organised. We all manage risk differently, think about it differently, and write it down differently. We could be a lot better at thinking about risk in a more structured way, where we could be working together to consider risks. If we take as an example, our efforts in identifying similar risks, or risks that cut across IFRC (say fraud risks or limited partner capacity), or risks that can only be managed by offices and operational teams working together (such as addressing the risk emerging from COVID-19 or addressing the global issue of gender disparity). We need to develop ways of working together to systematically ensure that these risks are better identified and managed through a more formal risk management process or system.
Delegation and escalation
A good risk management process allows risks that are being identified at operational levels, at programme level, in an office for example, to be flagged across the organisation. At the moment we are not always good at being open, sharing, collaborating, and lesson learning from our risk management decisions. The process should then provide a basis for management and senior staff to be informed of these risks, to enable them to use their resources to manage it. For example, country level donor disputes or demands could be a problem that other teams or other offices face. This could be escalated so that senior managers or the teams in IFRC that oversee the relationship with that donor could work HQ to HQ level, to promote improvement or resolve issues. Similarly there may be risks identified at the centre, perhaps a new type of fraud or a risk identified from emerging research, that project managers and all office staff should know and be aware of.
Risk appetite or tolerance
While IFRC manages risk, we are not very clear about the right level of risk that we can accept in order to achieve our objectives. The IFRC has to work in the world’s most toughest places and tackles the most complex issues, so risk is a normal and acceptable part of our work. Sometimes, things will go wrong. A good risk management system should help us to decide when and how much risk we could tolerate. It should tell us when we should do more to stop a risk from occurring, and when we should do less to save resources accepting that something potentially could go wrong. A clear risk appetite, where the organisation and our colleagues know what risks we are willing to take or tolerate is important. So for those ambitious, transformational projects in a country office, we might be willing to take higher risk and accept that they might fail, but the country office may want other projects to be implemented taking lower risk, so that the office will hit its overall objectives and targets. Risk appetite is the way we express this concept. We decide whether the level risk is acceptable or not by taking a view about whether, in this programme or activity, we think it is appropriate.
What are the actions we need to take to improve our risk management?
1) We need to have a common language of risk. This needs to be a simple framework that can be applied at a project, country office, regional and secretariat level. It needs to work for programme and corporate management. This document is the start of this process
2) We need to have a process that shares the risks we identify in programmes with our colleagues at an office level, and those at an office level at a regional level, and at a regional level with the corporate senior management team. The process will be supported by the recruitment of regional risk management officers who will escalate risk to the Geneva based Risk Management Senior Officer.
3) We need to all consider, document, and understand what risks are above our tolerance or appetite level against each of the agreed six risk categories, and then show how we are managing them. This ‘risk appetite’ should be understood and justified.
5) We should all commit to being trained and educated on risk management. We can all enhance our abilities and skills in this area. The new risk management officers will facilitates ongoing training and development for risk management across IFRC.
6) We need to understand, assess and evaluate how our national society partners manage, assess and understand risk. We should decide whether they are capable and work with them to enhance their capacity to achieve our shared objectives.
Summary
The IFRC does not want to avoid risk. Nor does it need a bureaucratic system to bear down on risk. It does, however, need a proportionate, principles-based, framework to manage risk effectively. The challenge is to create ‘smart risk rules’ to enable risk to be effectively and consciously managed and to provide a framework for us to work effectively together to do it. Like the fast sports car with big brakes, the risk management ‘brakes’ in IFRC are not there to slow the IFRC car down, but to enable it to be safely driven faster.

## Opportunities
Opportunity No. | Opportunity Event, Source & Impact (what can happen (event), how can that happen (source) and what will the impact be if it happens?) | Opportunity Description | Trigger | Possible Benefits | Inherent Impact (refer to matrix) | Inherent Likelihood (refer to matrix) | Inherent Opportunity Rating (refer to matrix) | Maximizing Actions (what's currently in place?) | Residual Impact (refer to matrix) | Residual Likelihood (refer to matrix) | Residual Opportunity Rating (refer to matrix) | Proposed Action | Person Responsible for Implementing Action/s | Implementation Date for Proposed Action/s | Status
1 | [6 empty] | 0 |  |  |  | 0
2 | [6 empty] | 0 |  |  |  | 0
3 | [6 empty] | 0 |  |  |  | 0
4 | [6 empty] | 0 |  |  |  | 0
5 | [6 empty] | 0 |  |  |  | 0
6 | [6 empty] | 0 |  |  |  | 0
7 | [6 empty] | 0 |  |  |  | 0
8 | [6 empty] | 0 |  |  |  | 0
9 | [6 empty] | 0 |  |  |  | 0
10 | [6 empty] | 0 |  |  |  | 0
11 | [6 empty] | 0 |  |  |  | 0
12 | [6 empty] | 0 |  |  |  | 0
13 | [6 empty] | 0 |  |  |  | 0
14 | [6 empty] | 0 |  |  |  | 0
15 | [6 empty] | 0 |  |  |  | 0
16 | [6 empty] | 0 |  |  |  | 0
17 | [6 empty] | 0 |  |  |  | 0
18 | [6 empty] | 0 |  |  |  | 0
19 | [6 empty] | 0 |  |  |  | 0
20 | [6 empty] | 0 |  |  |  | 0
21 | [6 empty] | 0 |  |  |  | 0
22 | [6 empty] | 0 |  |  |  | 0
23 | [6 empty] | 0 |  |  |  | 0
24 | [6 empty] | 0 |  |  |  | 0
25 | [6 empty] | 0 |  |  |  | 0
26 | [6 empty] | 0 |  |  |  | 0
27 | [6 empty] | 0 |  |  |  | 0
28 | [6 empty] | 0 |  |  |  | 0
29 | [6 empty] | 0 |  |  |  | 0
30 | [6 empty] | 0 |  |  |  | 0
31 | [6 empty] | 0 |  |  |  | 0
32 | [6 empty] | 0 |  |  |  | 0
33 | [6 empty] | 0 |  |  |  | 0
34 | [6 empty] | 0 |  |  |  | 0
35 | [6 empty] | 0 |  |  |  | 0
36 | [6 empty] | 0 |  |  |  | 0
37 | [6 empty] | 0 |  |  |  | 0
38 | [6 empty] | 0 |  |  |  | 0
39 | [6 empty] | 0 |  |  |  | 0
Impact
Opportunities
| Likelihood | Extreme (5) | Major (4) | Significant (3) | Minor (2) | Insignificant (1)
| Almost Certain (5) | High (25) | High (20) | High (15) | Medium (10) | Medium (5)
| Likely (4) | High(20) | High (16) | High (12) | Medium (8) | Medium (4)
| Possible (3) | High (15) | High (12) | Medium (9) | Medium (6) | Medium (3)
| Unlikely (2) | Medium (10) | Medium (8) | Medium (6) | Low (4) | Low (2)
| Rare (1) | Medium (5) | Medium (4) | Low (3) | Low (2) | Low(1)

## Version History
Time | Version
2020-05-01 | Version 1.0
2021-01-01 | Version 1.1
2021-02-01 | Version 1.11 | Updated conditional formatting
2021-07-01 | Version 1.12 | Included the enablers for the strategic priorities
2021-11-01 | Version 1.13 | Added "Safeguarding" to the risk category name
2022-05-01 | Version 1.15 | Added Strategic as a risk category

## Drop Down Value
Probability / Impact Scale | Proximity Scale | Acceptable Risk | Risk Response | Control Effectiveness | Risk Status | Risk Trend | Strategic Priority
1 | Within 1 month | Y | Treat | Very good | Open | Increasing | Climate and environmental crises
2 | Within 3 months | N | Tolerate | Good | Closed | Constant | Evolving crisis and disasters
3 | Within 6 months |  | Transfer | Satisfactory |  | Decreasing | Growing gaps in health and well-being
4 | Greater than 6 months |  | Terminate | Weak |  |  | Migration and identity
5 |  |  | Take more | Ineffective |  |  | Values, power and inclusion
|  |  |  | No controls |  |  | Enabler 1: Engaged
Enabler 2: Accountable
Enabler 3: Trusted