## Risk Matrix
Tool 2.1.9 Programmatic Risk Register
Note: Although this template is based upon the IFRC Operational Risk Template, it can also be used at a programmatic level. It is quite a detailed risk register template.
LIKELIHOOD | Risk Matrix
[10 empty] | Risk category | Clue
| Event is expected to occur in most circumstances | >90% | Almost Certain | 5 | [5 empty] | Contextual | Refers to events, factors or dynamics occurring in the broader environment which affect programming or operations yet are beyond the full control of IFRC (Political unrest, economic failure, famine, war, etc.). PESTEL is a helpful tool for assessment of context risk (political, economic, social, technological, environmental, legal)
| Event could occur probably in most circumstances | 75-90% | Highly Likely | 4 | [5 empty] | Programme Delivery | Future events may negatively impact a program’s performance, schedule, cost. Also includes the risk that our programmes cause harm to our beneficiaries or their environments.
| Event should occur at some time | 50-75% | Likely | 3 | [5 empty] | Fiduciary | The risk that funds, goods and services are not used for the intended purposes; do not achieve value for money, and are not adequately accounted for (included risk relating to fraud and corruption).
| Event could occur at some time | 20-50% | Possible | 2 | [5 empty] | Operational | The risks to IFRC objectives arising from inadequate or failed internal processes (procurement, HR, Finance, IT etc.); inadequate or people and resourcing risks (includes risk from commercial disputes, staff shortages, supply chain shortages, staff safety, partner capacity etc.).
| Event may occur only in exceptional circumstances | <20% | Unlikely | 1 | [5 empty] | Reputational | The potential for negative publicity, or uncontrollable events to harm IFRC’s reputation (global, regionally or in-country), therefore affecting our ability to complete our mission (loss of donor support, partner/government disengagement, beneficiary distrust etc.).
[5 empty] | 1 | 2 | 3 | 4 | 5 | Safeguarding (Sexual exploitation and abuse (external) and sexual harassment (internal)) | The risk that our staff, partner staff, volunteers, or beneficiaries suffer sexual exploitation, abuse, or harassment due to IFRC funding or operations.
[5 empty] | Insignificant | Minor | Moderate | Major | Severe | Strategic | Inappropriate policies, failure to meet expectations/requirements of NS/donors and other stakeholders.
|  |  | Missed Targets |  | 0-5% | 5-10% | 10-20% | 20-30% | More than 40%
|  |  | Reputation |  | Internal publicity | National publicity (instance) | Extended national publicity | International publicity (instance) | Extended international publicity | Note - The list is not exhaustive and risks can fit into more than one category. The focus should be on capturing the risk and recognising that risk can, and does happen throughout the strategic ,tactical or programme life cycle
|  |  | Compliance |  | Minor admonition | Minor penalties | Major penalties | Major censure | Closure
|  |  | Safety and Security |  | Minor injury | Serious injury | Multiple injuries | Single death | Multiple deaths
|  |  | Financial (% of reserves, USD) |  | 0.1% 60,000 | 0.1 to 1% 60 - 600,000 | 1-5% 600,000 - 3 Mi. | 5-25% 3 - 15 Mi. | More than 25% more than 15 Mi.
|  |  | Financial (% of program budget) |  | 0.1% | 0.1 to 1% | 1-5% | 5-25% | More than 25%
|  |  | Management Effort required to manage the impact of the event |  | Event managed through normal activity | Event whose consequencies are absorbed by additional management effort | Significant event that is managed by little additional effort | Significant event that needs substantial management effort | Catastrophic event forcing closure
IMPACT

## Introduction to risk management (hidden)
Introduction
Risk management should be one of the cornerstone of IFRC good governance and sound management structures. It should provide the framework within which the achievement of IFRC’s objectives are managed and delivered. IFRC takes its responsibilities to its beneficiaries, partners, and donors seriously, and regards risk management as a tool of good management and an important factor in ensuring that we meet our obligations to the Movement donors and ultimately our beneficiaries.
Purpose of refreshing our risk management approach
This template is designed to:
1) Start the process of promoting and expanding the guidance to IFRC staff on the risk management processes..
2) Set out the de-minimis features of the framework and the structure of risk management within the Federation.
3) Provide a standardised template for the identification and documentation of risks, in a standard risk register.
4) Develop common terminology for risk management in IFRC.
Where are we on risk?
We all manage risk at work and in our daily lives. For example we consider the impact and likelihood of rain and decide whether to purchase or take an umbrella with us. This is true in our work lives too. IFRC manages risk every day through its country offices, regional offices and central corporate and operational teams - steered by the Senior Management Team and the Board. Risks flow from objectives and represent the uncertainty around the achievement of objectives. Despite IFRC being highly ambitious, it has been able to avoid significant risks coming to fruition and significant failures occurring. So we are collectively managing risk. IFRC is also naturally resistant to risk as our project portfolios have a hedge effect (it is hard for everything to go wrong at once). This makes IFRC more risk resilient. Over time, donor expectations have grown to expect a more formalised approach to risk management. Additionally the complexity, reach, and ambition of the Federation has grown to a point where a more standardised approach to risk management is needed.
What can we do better?
Systematisation
Whilst IFRC undertakes risk management activities, these lack systematisation and coherence across the organisation. Some risks are more structured in their management than others. For example, duty of care and security risks are more strongly controlled, and our efforts to manage it is more organised. Business risks (that is general risks to our objectives, most often project delivery objectives) are less organised. We all manage risk differently, think about it differently, and write it down differently. We could be a lot better at thinking about risk in a more structured way, where we could be working together to consider risks. If we take as an example, our efforts in identifying similar risks, or risks that cut across IFRC (say fraud risks or limited partner capacity), or risks that can only be managed by offices and operational teams working together (such as addressing the risk emerging from COVID-19 or addressing the global issue of gender disparity). We need to develop ways of working together to systematically ensure that these risks are better identified and managed through a more formal risk management process or system.
Delegation and escalation
A good risk management process allows risks that are being identified at operational levels, at programme level, in an office for example, to be flagged across the organisation. At the moment we are not always good at being open, sharing, collaborating, and lesson learning from our risk management decisions. The process should then provide a basis for management and senior staff to be informed of these risks, to enable them to use their resources to manage it. For example, country level donor disputes or demands could be a problem that other teams or other offices face. This could be escalated so that senior managers or the teams in IFRC that oversee the relationship with that donor could work HQ to HQ level, to promote improvement or resolve issues. Similarly there may be risks identified at the centre, perhaps a new type of fraud or a risk identified from emerging research, that project managers and all office staff should know and be aware of.
Risk appetite or tolerance
While IFRC manages risk, we are not very clear about the right level of risk that we can accept in order to achieve our objectives. The IFRC has to work in the world’s most toughest places and tackles the most complex issues, so risk is a normal and acceptable part of our work. Sometimes, things will go wrong. A good risk management system should help us to decide when and how much risk we could tolerate. It should tell us when we should do more to stop a risk from occurring, and when we should do less to save resources accepting that something potentially could go wrong. A clear risk appetite, where the organisation and our colleagues know what risks we are willing to take or tolerate is important. So for those ambitious, transformational projects in a country office, we might be willing to take higher risk and accept that they might fail, but the country office may want other projects to be implemented taking lower risk, so that the office will hit its overall objectives and targets. Risk appetite is the way we express this concept. We decide whether the level risk is acceptable or not by taking a view about whether, in this programme or activity, we think it is appropriate.
What are the actions we need to take to improve our risk management?
1) We need to have a common language of risk. This needs to be a simple framework that can be applied at a project, country office, regional and secretariat level. It needs to work for programme and corporate management. This document is the start of this process
2) We need to have a process that shares the risks we identify in programmes with our colleagues at an office level, and those at an office level at a regional level, and at a regional level with the corporate senior management team. The process will be supported by the recruitment of regional risk management officers who will escalate risk to the Geneva based Risk Management Senior Officer.
3) We need to all consider, document, and understand what risks are above our tolerance or appetite level against each of the agreed six risk categories, and then show how we are managing them. This ‘risk appetite’ should be understood and justified.
5) We should all commit to being trained and educated on risk management. We can all enhance our abilities and skills in this area. The new risk management officers will facilitates ongoing training and development for risk management across IFRC.
6) We need to understand, assess and evaluate how our national society partners manage, assess and understand risk. We should decide whether they are capable and work with them to enhance their capacity to achieve our shared objectives.
Summary
The IFRC does not want to avoid risk. Nor does it need a bureaucratic system to bear down on risk. It does, however, need a proportionate, principles-based, framework to manage risk effectively. The challenge is to create ‘smart risk rules’ to enable risk to be effectively and consciously managed and to provide a framework for us to work effectively together to do it. Like the fast sports car with big brakes, the risk management ‘brakes’ in IFRC are not there to slow the IFRC car down, but to enable it to be safely driven faster.

## Dont Change!
Probability / Impact Scale | Impact | Proximity Scale | Acceptable Risk | Risk Response | Control Effectiveness | Risk Status | Risk Trend | Strategic Priority
Unlikely | Insignificant | Within 1 month | Y | Treat | Very good | Open | Increasing | Climate and environmental crises
Possible | Minor | Within 3 months | N | Tolerate | Good | Closed | Constant | Evolving crisis and disasters
Likely | Moderate | Within 6 months |  | Transfer | Satisfactory |  | Decreasing | Growing gaps in health and well-being
Highly Likely | Major | Greater than 6 months |  | Terminate | Weak |  |  | Migration and identity
Almost Certain | Severe |  |  | Take more | Ineffective |  |  | Values, power and inclusion
[5 empty] | No controls |  |  | Enabler 1: Engaged
Enabler 2: Accountable
Contextual | [7 empty] | Enabler 3: Trusted
Programme Delivery
Operational
Fiduciary
Safeguarding
Reputational
Strategic
Almost Certain Insignificant | Major
Highly LikelyInsignificant | Moderate
LikelyInsignificant | Minor
PossibleInsignificant | Minor
UnlikelyInsignificant | Minor
Almost CertainMinor | Major
HighlyLikelyMinor | Major
LikelyMinor | Moderate
PossibleMinor | Minor
UnlikelyMinor | Minor
Almost CertainModerate | Severe
Highly LikelyModerate | Major
LikelyModerate | Major
PossibleModerate | Moderate
UnlikelyModerate | Minor
Almost CertainMajor | Severe
Highly LikelyMajor | Severe
LikelyMajor | Major
PossibleMajor | Major
UnlikelyMajor | Moderate
Almost CertainSevere | Severe
Highly LikelySevere | Severe | *
LikelySevere | Severe
PossibleSevere | Major | *
UnlikelySevere | Major

## Programmatic Risk Register
Risk no: | Sector | Risk Category | Risk Driver / Root cause | Risk description | Risk consequences / Impact | Inherent Likelihood | Inherent Impact | Inherent Risk Factor | Current Controls (Mitigation) | Residual Likelihood | Residual Impact | Residual Risk Factor | Additional controls to be put in place / progress in implementing mitigations. | Estimated implementation date of additional controls | Proximity | Risk Response Strategy | Risk owner | Risk Trend | Last Updated | cross-ref
1 | [7 empty] | #N/A |  |  |  | #N/A
2 | [7 empty] | #N/A |  |  |  | #N/A
3 | [7 empty] | #N/A |  |  |  | #N/A
4 | [7 empty] | #N/A |  |  |  | #N/A
5 | [7 empty] | #N/A |  |  |  | #N/A
8 | [7 empty] | #N/A |  |  |  | #N/A
9 | [7 empty] | #N/A |  |  |  | #N/A
10 | [7 empty] | #N/A |  |  |  | #N/A
11 | [7 empty] | #N/A |  |  |  | #N/A
12 | [7 empty] | #N/A |  |  |  | #N/A
13 | [7 empty] | #N/A |  |  |  | #N/A
14 | [7 empty] | #N/A |  |  |  | #N/A
15 | [7 empty] | #N/A |  |  |  | #N/A
16 | [7 empty] | #N/A |  |  |  | #N/A
17 | [7 empty] | #N/A |  |  |  | #N/A
18 | [7 empty] | #N/A |  |  |  | #N/A
19 | [7 empty] | #N/A |  |  |  | #N/A
20 | [7 empty] | #N/A |  |  |  | #N/A
21 | [7 empty] | #N/A |  |  |  | #N/A
22 | [7 empty] | #N/A |  |  |  | #N/A
23 | [7 empty] | #N/A |  |  |  | #N/A
24 | [7 empty] | #N/A |  |  |  | #N/A
25 | [7 empty] | #N/A |  |  |  | #N/A
26 | [7 empty] | #N/A |  |  |  | #N/A
28 | [7 empty] | #N/A |  |  |  | #N/A
29 | [7 empty] | #N/A |  |  |  | #N/A
31 | [7 empty] | #N/A |  |  |  | #N/A
32 | [7 empty] | #N/A |  |  |  | #N/A
[8 empty] | #N/A |  |  |  | #N/A
[8 empty] | #N/A |  |  |  | #N/A
[8 empty] | #N/A |  |  |  | #N/A
[8 empty] | #N/A |  |  |  | #N/A
[8 empty] | #N/A |  |  |  | #N/A
[8 empty] | #N/A |  |  |  | #N/A
[8 empty] | #N/A |  |  |  | #N/A
[8 empty] | #N/A |  |  |  | #N/A
[8 empty] | #N/A |  |  |  | #N/A
[8 empty] | #N/A |  |  |  | #N/A
[8 empty] | #N/A |  |  |  | #N/A
[8 empty] | #N/A |  |  |  | #N/A
[8 empty] | #N/A |  |  |  | #N/A
[8 empty] | #N/A |  |  |  | #N/A
[8 empty] | 0 |  |  |  |  | #N/A
Note on B1: What sector / programme is the risk relevant to?
Note on C1: Choose the best fit from one of the 7 drop-down options using the category definitions (see the 'risk matrix tab for reference)
Note on D1: What is causing the risk to occur? List the main risk drivers in bullet points.
Note on E1: What is the risk (i.e. the event that might occur?) Set out a clear and concise description of the risk event.
Note on F1: What are the consequences of the risk event on the objectives of our operations / programmes / organisation?
Note on G1: Likelihood of risk materialising before you take action / put mitigation in place.
Note on H1: Impact of risk materialising before you take action / put in place mitigation
Note on I1: Autofills based on likelihood & impact
Note on J1: Set out the actions you are taking to treat the risk. Try to be as specific - (e.g. instead of 'ongoing discussions' list the key forums for discussion, how often they take place etc.)
Note on K1: Likelihood of the risk occuring after you have taken action to address it.
Note on L1: Impact of the risk after you have taken action to treat the risk.
Note on M1: Dominika ABIDI: Autofils based on residual likelihood / impact.
Note on N1: Set out progress in implementing mitigations listed in column I / List all the mitigating actions you are planning to put in place including those that are only partially implemented.
Note on O1: Timelines for implementing additional actions.
Note on R1: Add the name of the individual(s) who take responsibility for treating the risk.
Note on U1: cross-ref to relevant challenges from the Market place exercise at Ops Mng workshop.