## Activity Schedule
Example 2.2.1 - Gantt Chart
Note: an artificial example of top line activities related to the first 6 months of a rental assistance programme
Rental Assistance Activity Schedule - Example First 6 months Top-line Activity Schedule
Week
Ref | Activity Description | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
Coordination
Shelter surge capacity arrives | bar: Week 1
Internal advocacy - NS (HQ) & IFRC | bar: Week 1 to Week 2
Engagement with NS branches | bar: Week 3
Engagement with authorities / sector/ civil society on rental assistance | bar: Week 2; Week 4; Week 6; Week 8; Week 10; Week 12; Week 14; Week 16; Week 18; Week 20; Week 22; Week 24; Week 26
Context Analysis
Rapid (general) shelter needs assessment | bar: Week 2 to Week 3
Vulnerabilities, needs and capacities | bar: Week 3
National society capacity assessment | bar: Week 3
Shelter response options analysis | bar: Week 3 to Week 4
CVA feasibility assessment | bar: Week 4
Rental housing market assessment | bar: Week 4
Security of tenure assessment | bar: Week 4
Programme risk assessment | bar: Week 4 to Week 5
Programme Design & Planning
Recruitment of shelter manager (HQ) | bar: Week 5 to Week 8
Programme design (incl. consultations) | bar: Week 5 to Week 9
Approvals | bar: Week 8 to Week 10
Advocacy | bar: Week 8 to Week 10
Information management system design | bar: Week 10 to Week 15
Recruitment | bar: Week 10 to Week 13
Training of key staff | bar: Week 14 to Week 15
Implimentation
Community Engagement & Accountability Activities | bar: Week 14 to Week 26
Case Identification | bar: Week 15 to Week 26
Registration | bar: Week 17 to Week 26
Selection | bar: Week 19 to Week 26
Household orientation | bar: Week 21 to Week 26
Housing standards verification | bar: Week 22 to Week 26
Tenure security verification | bar: Week 22 to Week 26
Property owner orientation | bar: Week 22 to Week 26
Enrolment on programme & programme agreements | bar: Week 23 to Week 26
Payment support | bar: Week 23 to Week 26
Casework | bar: Week 23 to Week 26
Monitoring | bar: Week 23 to Week 26
Rental market monitoring | bar: Week 25 to Week 26
Exit strategy monitoring | bar: Week 23 to Week 26
Risk monitoring
Reporting, Evaluation, Learning
Reporting
Evaluation
Learning