## Gantt
Example 2.2.1 - Plan of action for Rental Assistance
Note: This is real example of a plan of action developed in Slovakia
Task / Activity | Person in charge | Approx. date of finalization | 2022-07-01 |  |  |  | 2022-08-01 |  |  |  | 2022-09-01 |  |  |  |  | 2022-10-01 |  |  |  | 2022-11-01 |  |  |  | 2022-12-01 |  |  |  |  | 2023-01-01 |  |  |  | 2023-02-01 |  |  |  | 2023-03-01 |  |  |  |  | 2023-04-01 |  |  |  | 2023-05-01 |  |  |  |  | 2023-06-01 |  |  |  | 2023-07-01 |  |  |  | 2023-08-01 |  |  |  |  | 2023-09-01
|  |  | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4
Preparation
Eligibility and selection
Analyse rapid / detailed assessment information | bar: 2022-07-01 W1 to 2022-07-01 W2
Define targeting strategy and eligibility criteria for the shelter programme (scoring matrix based on priority socio economic vulnerabilities) | bar: 2022-07-01 W2 to 2022-07-01 W4
Develop shelter operational plan and budget (rationale, shelter assistance options and modalities, HR plan, timeframe, overall budget) | bar: 2022-07-01 W3 to 2022-08-01 W2
Present shelter plan & budget to NS | bar: 2022-07-01 W2; 2022-07-01 W4
NS to launch nat staff recruitment (as per HR plan) | bar: 2022-07-01 W4 to 2022-08-01 W4
Develop & translate SOPs (forms and tools to use): registration, scoring, application, housing adequacy checklist, monitoring checklist | bar: 2022-07-01 W4 to 2022-08-01 W3
Establish IM system for registration, database and case management, payment and montioring (kobo + Espo CRM + RedRose) | bar: 2022-08-01 W3 to 2022-09-01 W3
Develop legal paperwork - Bipartite agreements SRC-landlord and SRC-tenant in both host family arrangement and rental assistance - Standard rental contract between Landlord and Tenant (SRC not involved) | bar: 2022-08-01 W2 to 2022-09-01 W1
Develop SRC staff/volunteers orientation package (session and simulation exercise) | bar: 2022-09-01 W1
Implementation
Pilot phase - one location - one branch - max 25 HHs selected
Staff orientation and simulation sessions | bar: 2022-09-01 W2
Registration at the Humanitarian Service Point (HSP) | bar: 2022-09-01 W2; 2022-10-01 W1
Beneficiary selection (analysis of scoring and vulnerabilities) | bar: 2022-09-01 W3; 2022-10-01 W2
Housing adequacy visits | bar: 2022-09-01 W4 to 2022-10-01 W2
Enrollment at the HSP - application form, signature of contract / agreements, copie of documents etc. | bar: 2022-09-01 W5 to 2022-10-01 W2
Payment |  |  | 2022-10-01 W1: 1.1; 2022-10-01 W3: 2.1; 2022-11-01 W1: 1.2; 2022-11-01 W3: 2.2; 2022-12-01 W1: 1.3; 2022-12-01 W3: 2.3; 2023-01-01 W1: 1.4; 2023-01-01 W3: 2.4; 2023-02-01 W1: 1.5; 2023-02-01 W3: 2.5; 2023-03-01 W1: 1.6; 2023-03-01 W3: 2.6
Monitoring visit | bar: 2022-10-01 W2; 2022-10-01 W4; 2022-11-01 W2; 2022-11-01 W4; 2022-12-01 W2; 2022-12-01 W5; 2023-01-01 W2; 2023-01-01 W4; 2023-02-01 W2; 2023-02-01 W4; 2023-03-01 W2
Request for payment | bar: 2022-12-01 W1
Rollout phase - six branches - 975 HHs selected
Staff orientation and simulation sessions | bar: 2022-10-01 W2 to 2022-11-01 W3
Registration at the Humanitarian Service Point (HSP) | bar: 2022-10-01 W3 to 2023-02-01 W2
Beneficiary selection (analysis of scoring and vulnerabilities) | bar: 2022-10-01 W3 to 2023-02-01 W2
Housing adequacy visits | bar: 2022-10-01 W4 to 2023-02-01 W2
Enrollment at the HSP - application form, signature of contract / agreements, copie of documents etc. | bar: 2022-10-01 W4 to 2023-02-01 W2
Request for payment (1st payment)
Payment | bar: 2022-11-01 W1; 2022-11-01 W3; 2022-12-01 W1; 2022-12-01 W3; 2023-01-01 W1; 2023-01-01 W3; 2023-02-01 W1; 2023-02-01 W3; 2023-03-01 W1; 2023-03-01 W3; 2023-03-01 W5; 2023-04-01 W2; 2023-04-01 W4; 2023-05-01 W2; 2023-05-01 W4; 2023-06-01 W1; 2023-06-01 W3; 2023-07-01 W1; 2023-07-01 W3; 2023-08-01 W1; 2023-08-01 W3
Monitoring visit | bar: 2022-11-01 W2; 2022-11-01 W4; 2022-12-01 W2; 2022-12-01 W5; 2023-01-01 W2; 2023-01-01 W4; 2023-02-01 W2; 2023-02-01 W4; 2023-03-01 W2; 2023-03-01 W4; 2023-04-01 W1; 2023-04-01 W3; 2023-05-01 W1; 2023-05-01 W3; 2023-05-01 W5; 2023-06-01 W2; 2023-06-01 W4; 2023-07-01 W2; 2023-07-01 W4; 2023-08-01 W2
Exit strategy

## HR plan
Task | Modality | Target HHs | HR needs | Duration
Pilot phase | Registration
| House adequacy visits | 25
| Monitoring | 25
Roll out | Registration
| House adequacy visits | 1025
| Monitoring | 1025

## Budget 1 (hidden)
Cat. | Description | Quantity | Unit | Unit Cost | Times | Unit | Total Cost | Comments
Rental | Conditional cash grant for rental assistance | 500 | Household | 620.8333 | 6 | month | 1862500 | 450 - 600 - 700 EUR /mo 500 - 675 - 800 EUR /mo |  | OANDA Rate | EUR > CHF | 0.96758
| One-off payment of security deposit for rental assistance | 500 | Household | 620.8333 | 1 | month | 310416.6667 | in one tranche with first payment |  |  | CHF > EUR | 1.0333
| Extension of rental assistance for very vulnerable cases (3 months) | 125 | Household | 620.8333 | 3 | month | 232812.5
Host | Conditional cash grant for host family assistance - hosting TP holders | 450 | Household | 112 | 6 | month | 302400
| Conditional cash grant for host family assistance - hosting non TP holders | 50 | Household | 858 | 6 | month | 257400
| Extension of host family support for very vulnerable cases (25% of caseload = 125HHs) | 125 | Household | 23325 | 3 | month | 69975
Top-ups | Winterization grant | 1000 | Household | 300 | 1 |  | 300000 | In november
| Disability / adaptation top-up (15% of HHs) | 150 | Household | 500 | 1 |  | 75000 | Upon housing adequacy visit
| Household items needs top-up | 500 | Household | 300
| Housing adequacy needs top-up | 500 | Household | 500
| Housing adequacy / HH items top up | 1000 | Household | 400 | 1 |  | 400000 | Contingent upon housing adequacy visit
Fees | RedRose fees | 6750 | Transaction | 2.5 |  |  | 16875 | Winter top up incl in the 3rd tranche, deposit and HH items top up incl in the 1st tranche
| RedRose exchange rate loss (CHF and Euro) |  |  | 1% |  |  | 38105.0417
| SUB TOTAL | [5 empty] | 3865484.2083 | 3740165.2103
|  |  |  | EA budget | OANDA rate 18/08/2022 |  | 3916658.224 | 3790400 | shelter + RR fees
Activities | Application /website for HH registration to offer host arrangements, HSP appointments, request housing etc. | 1 | Lumpsum | 15000 |  |  |  | 103900
| Programme orientation & simulation in 6 branches (travels, accomm, materials) | 1 | Lumpsum | 2500
| Volunteers monitoring and visits for 6 branches (transport, per diem, payments) | 1 | Lumpsum | 86400
NS dev & learning | Country-level lessons learned workshop | 1 | Lumpsum | 5000 |  |  |  | 153000
| Programme evaluation - Final / through consultancy | 1 | Lumpsum | 20000
| Video case studies / case studies on hosting arrangements incl. Referral mechanisms, CEA and PGI mainstreaming | 1 | Lumpsum | 25000
| STT training for 2 SRC staff (ops man and SI officer - HQ) | 1 | Lumpsum | 10000
| NS staff training on CEA (online information sharing mechanisms) | 1 | Lumpsum | 7000
| Translation of NS volunteer development package (WORK; stay safe and all core IFRC learning courses) this can include all shelter online courses | 1 | Lumpsum | 86000
Supplies and services? | Translation services (technical guidelines, SOPs, orientation manual, training materials) |  |  | 30000 |  |  |  | 165840
| Live translation in to Slovak (interpreters) |  |  | 15000
| Local rental of vhl for monitoring and fuel |  |  | 79200
| Training materials for all branches |  |  | 6000
| Laptops |  |  | 27000
| 24 Mobiles - data plan for 12 months |  |  | 8640
Staff costs | Nat Inclusion coord (HQ) | 1 | people | 2400 | 6 | month | 14400 | 270000
| Nat Inclusion officer | 9 | people | 2200 | 6 | month | 118800
| Liaison officers | 6 | people | 1800 | 6 | month | 64800
| HSP officer | 6 | people | 2000 | 6 | month | 72000
Note on B26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: for the entire operation
Note on C8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: now only for host (500HHs)
Note on C9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 15% of HH selected
Note on C10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: now only for rental, 300EUR
Note on C11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: now for host fam, 100% 500EUR

## Budget 2 - Just Host top up (hidden)
Cat. | Description | Quantity | Unit | Unit Cost | Times | Unit | Total Cost | Comments
Rental | Conditional cash grant for rental assistance | 500 | Household | 620.8333 | 6 | month | 1862500 | 450 - 600 - 700 EUR /mo 500 - 675 - 800 EUR /mo |  | OANDA Rate | EUR > CHF | 0.96758
| One-off payment of security deposit for rental assistance | 500 | Household | 620.8333 | 1 | month | 310416.6667 | in one tranche with first payment |  |  | CHF > EUR | 1.0333
| Extension of rental assistance for very vulnerable cases (3 months) | 125 | Household | 620.8333 | 3 | month | 232812.5
Host | Conditional cash grant for host family assistance - hosting TP holders | 700 | Household | 112 | 6 | month | 470400
| Conditional cash grant for host family assistance - hosting non TP holders | 0 | Household | 858 | 6 | month | 0 |  |  | 257400
| Extension of host family support for very vulnerable cases (25% of caseload = 125HHs) | 175 | Household | 112 | 3 | month | 336
Top-ups | Winterization grant | 1200 | Household | 300 | 1 |  | 360000 | In november
| Disability / adaptation top-up (15% of HHs) | 180 | Household | 500 | 1 |  | 90000 | Upon housing adequacy visit
| Household items needs top-up | 500 | Household | 300
| Housing adequacy needs top-up | 500 | Household | 500
| Housing adequacy / HH items top up | 1200 | Household | 400 | 1 |  | 480000 | Contingent upon housing adequacy visit
Fees | RedRose fees | 8100 | Transaction | 2.5 |  |  | 20250
| RedRose exchange rate loss (CHF and Euro) |  |  | 1% |  |  | 38064.6517
| SUB TOTAL | [5 empty] | 3864779.8183 | 3739483.6566 |  | 3870484
|  |  |  | EA budget | OANDA rate 18/08/2022 |  | 3916658.224 | 3790400 | shelter + RR fees
Activities | Application /website for HH registration to offer host arrangements, HSP appointments, request housing etc. | 1 | Lumpsum | 15000 |  |  |  | 103900
| Programme orientation & simulation in 6 branches (travels, accomm, materials) | 1 | Lumpsum | 2500
| Volunteers monitoring and visits for 6 branches (transport, per diem, payments) | 1 | Lumpsum | 86400
NS dev & learning | Country-level lessons learned workshop | 1 | Lumpsum | 5000 |  |  |  | 153000
| Programme evaluation - Final / through consultancy | 1 | Lumpsum | 20000
| Video case studies / case studies on hosting arrangements incl. Referral mechanisms, CEA and PGI mainstreaming | 1 | Lumpsum | 25000
| STT training for 2 SRC staff (ops man and SI officer - HQ) | 1 | Lumpsum | 10000
| NS staff training on CEA (online information sharing mechanisms) | 1 | Lumpsum | 7000
| Translation of NS volunteer development package (WORK; stay safe and all core IFRC learning courses) this can include all shelter online courses | 1 | Lumpsum | 86000
Supplies and services? | Translation services (technical guidelines, SOPs, orientation manual, training materials) |  |  | 30000 |  |  |  | 165840
| Live translation in to Slovak (interpreters) |  |  | 15000
| Local rental of vhl for monitoring and fuel |  |  | 79200
| Training materials for all branches |  |  | 6000
| Laptops |  |  | 27000
| 24 Mobiles - data plan for 12 months |  |  | 8640
Staff costs | Nat Inclusion coord (HQ) | 1 | people | 2400 | 6 | month | 14400 | 270000
| Nat Inclusion officer | 9 | people | 2200 | 6 | month | 118800
| Liaison officers | 6 | people | 1800 | 6 | month | 64800
| HSP officer | 6 | people | 2000 | 6 | month | 72000
Note on B26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: for the entire operation
Note on C8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: now only for host (500HHs)
Note on C9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 15% of HH selected
Note on C10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: now only for rental, 300EUR
Note on C11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: now for host fam, 100% 500EUR

## Budget 3 with SK renters
Cat. | Description | Quantity | Unit | Unit Cost | Times | Unit | Total Cost | Comments
Rental | Conditional cash grant for rental assistance | 500 | Household | 620.8333 | 6 | month | 1862500 | 450 - 600 - 700 EUR /mo 500 - 675 - 800 EUR /mo | OANDA Rate | EUR > CHF | 0.96758
| One-off payment of security deposit for rental assistance | 500 | Household | 620.8333 | 1 | month | 310416.6667 | in one tranche with first payment |  | CHF > EUR | 1.0333 | 1.068
| Conditional cash grant for rental assistance (Slovak HH) | 50 | Household | 620.8333 | 6 | month | 186250 | 10% of 500 HHs
| One-off payment of security deposit for rental assistance (Slovak HH) | 50 | Household | 620.8333 | 1 | month | 31041.6667
| Extension of rental assistance for very vulnerable cases (3 months) | 137.5 | Household | 620.8333 | 3 | month | 256093.75 | 25% of total rental caseload | 257400
Host | Conditional cash grant for host family assistance - hosting TP holders | 500 | Household | 112 | 6 | month | 336000
| Conditional cash grant for host family assistance - hosting non TP holders | 0 | Household | 858 | 6 | month | 0
| Extension of host family support for very vulnerable cases (25% of caseload) | 125 | Household | 112 | 3 | month | 42000
Top-ups | Winterization grant | 1050 | Household | 300 | 1 |  | 315000 | In november or february
| Disability / adaptation top-up | 150 | Household | 500 | 1 |  | 75000 | Upon housing adequacy visit
| Housing adequacy / HH items top up | 1050 | Household | 400 | 1 |  | 420000 | Contingent upon housing adequacy visit
Fees | RedRose fees | 7087.5 | Transaction | 2.5 |  |  | 17718.75
| RedRose exchange rate loss (CHF and Euro) |  |  | 1% |  |  | 38343.0208
| SUB TOTAL | [5 empty] | 3890363.8542 | 3764238.258
| DG HOME list of activities |  |  | EA budget | OANDA rate 18/08/2022 |  | 3916658.224 | 3790400
Activities | Application /website for HH registration to offer host arrangements, HSP appointments, request housing etc. | 1 | Lumpsum | 15000 |  |  |  | 103900
| Programme orientation & simulation in 6 branches (travels, accomm, materials) | 1 | Lumpsum | 2500
| Volunteers monitoring and visits for 6 branches (transport, per diem, payments) | 1 | Lumpsum | 86400
NS dev & learning | Country-level lessons learned workshop | 1 | Lumpsum | 5000 |  |  |  | 153000
| Programme evaluation - Final / through consultancy | 1 | Lumpsum | 20000
| Video case studies / case studies on hosting arrangements incl. Referral mechanisms, CEA and PGI mainstreaming | 1 | Lumpsum | 25000
| STT training for 2 SRC staff (ops man and SI officer - HQ) | 1 | Lumpsum | 10000
| NS staff training on CEA (online information sharing mechanisms) | 1 | Lumpsum | 7000
| Translation of NS volunteer development package (WORK; stay safe and all core IFRC learning courses) this can include all shelter online courses | 1 | Lumpsum | 86000
Supplies and services? | Translation services (technical guidelines, SOPs, orientation manual, training materials) |  |  | 30000 |  |  |  | 165840
| Live translation in to Slovak (interpreters) |  |  | 15000
| Local rental of vhl for monitoring and fuel |  |  | 79200
| Training materials for all branches |  |  | 6000
| Laptops |  |  | 27000
| 24 Mobiles - data plan for 12 months |  |  | 8640
Staff costs | Nat Inclusion coord (HQ) | 1 | people | 2400 | 6 | month | 14400 | 270000
| Nat Inclusion officer | 9 | people | 2200 | 6 | month | 118800
| Liaison officers | 6 | people | 1800 | 6 | month | 64800
| HSP officer | 6 | people | 2000 | 6 | month | 72000
Note on B26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: for the entire operation